## CHNA_ImplPlan_2020-22
CHNA Implementation Plan Tactics - Henry & Benton Counties MO
Wave #3 2019 CHNA Health Needs Tactics - Year 3 of 3 (Starting 1/1/2022 - 12/31/22) **Updated 01/07/2022
| CHNA Health Areas of Need | T | "Specific Actions" to Address Community Health Need or "Reasons Why Hospital Will Not" Address Need | Identified "Lead" | Identified Partners | Timeframe | GVMH Funding | Compass Funding | HCHC Funding | City of Clinton Funding | Schools Funding | Other Funding $$ | TOTAL | NOTES
1 | Mental Health School focused (Diagnosis, Treatment, Aftercare) / Suicides | a | Continue to build community BH education program. Collaborate with community elementary, middle and high schools to educate students on mental health (de-stigmatize mental health conditions, suicide prevention and social media bullying.) | Compass Schools | GVMH, Law Enforcement, MO, Cities, Counties, Colleges, HCHC, Kaysinger Basin, MU Ext, WCCAA | 01/01/20 - 12/31/20 |  | 33346 |  |  |  |  | 33346
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Maintain a community inventory of services to document the availability of mental health resources, including hours of service. Make BH inventory available to the public as needed. Document mental health services by age categories. |  |  |  |  | 1400000 |  |  |  |  | 1400000
|  | c | Continue mental health care support at clinics. Increase depression screenings by PCPs. Add trauma assessment for pediatrics and other MH issues. | [9 empty] | 0
|  | d | Investigate grant writing to fund mental health education and services. If available, designate community lead to attain the necessary grant. | [9 empty] | 0
|  | e | Partner to improve mental health service "first aid" training for law enforcement, schools and other first responders in the community. | Compass |  | 01/01/20 - 12/31/20 |  | 9129 |  |  |  |  | 9129
|  | f | Continue suicide prevention training at schools. Develop and sponsor an anti-suicide campaign for local community members. (Schools= $500 per kit each year.) | Compass/Schools |  | 01/01/20 - 12/31/20 |  | 4547 |  |  | 500 |  | 5047
|  | g | Educate GVMH staff regarding mental health service delivery. Create updated brochures on mental health services. Continue ED tele psych service offerings. | GVMH |  | 01/01/22 - 12/31/22 | 50000 | [5 empty] | 50000 | Complete for 2020, 2021 repeat in 2022
|  | h | Continue to grow school counselors (Compass partnership) in Clinton schools. Expand into Warsaw and Clinton school districts. Recruit for social workers, counselors and MH providers in schools. | Schools/ Compass | [8 empty] | 0
|  | i | Continue to have law enforcement/providers complete CIT training (20 hour training). | Law Enforcement/City |  | 2020 |  | 16413 |  | 3000 |  |  | 19413 | **City: Police time
|  | j | Encourage participation to attend monthly meetings (MissouriCIT.com). | [9 empty] | 0
|  | k | Continue with Compass crisis training on school campuses. | Compass | [8 empty] | 0
|  | l | Continue with MU ext. youth MH course offerings. | MU Ext | [8 empty] | 0
|  | m | Continue to offer and promote the QPR Compass program for community members. | Compass |  | 01/01/20 - 12/31/20 |  | 4547 |  |  |  |  | 4547
2 | Economic Development | a | Continue with Workforce Ready Community Assessment. Continue the PSA economic development advisory group to lead local efforts and actively recruit new businesses/retain existing businesses in the PSA. | Chamber (Clinton) / City of Warsaw | Cities, Kaysinger Basin, GVMH, MU Ext, Clergy, HCHC, Compass, MO, Providers, Royal Oaks, | [7 empty] | 0
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Continue to report PSA business retention and expansion data. Complete compliance checks for area businesses. | [9 empty] | 0
|  | c | Expand PSA economic development efforts to decrease poverty / increase access to health insurance. | [9 empty] | 0
|  | d | Encourage local businesses to host job fairs to promote their open positions for all education levels. (No degree, GED, etc.) | SFCC |  | 2020-03-01 | [5 empty] | 500 | 500 | TLF: All Companies in Benton and Henry Counties
|  | e | Continue to partner with Kaysinger Basin and understand their initiatives. Help further launch this support in Henry and Benton County. | SFCC |  | 2020-02-01 | [5 empty] | 100 | 100 | TLF: Warsaw, Cole Camp, Lincoln, Chambers, MU Ext
|  | f | Continue to provide labor information explaining skill level to recruit new businesses in Henry and Benton County. Identify incentives to attract and retain. | City |  | 01/01/20 - 12/31/20 |  |  |  | 24000 |  |  | 24000 | **25% of City budget
|  | g | Create county economic dev zone credit/apply for community benefit grant to finance. | [9 empty] | 0
|  | h | Continue to promote small business growth by securing grants/endowment funds (banking). | [9 empty] | 0
|  | i | Continue to host employable skills training and career fairs with high school/college students. Build a program in partnership with the chamber, hospital, career center, Kaysinger and other PSA businesses. | City / GVMH / SFCC |  | 2022-06-01 | 7200 |  |  | 24000 |  | 250 | 31450 | **25% of City budget TLF: MO One Start, Eco Dec, SBDC Programs, Referrals, trainings in Clinton - EXTENDED DUE TO COVID
|  | j | Continue with the existing business program study with surveying to retain and grow small businesses. Utilize job training funds. Launch this initiative in Benton Co. | City | [5 empty] | 48000 |  |  | 48000 | **50% of City budget
3 | Drugs (Opioids, Meth, Heroin, Marijuana) | a | Provide tobacco/drug/alcohol education to students (i.e. DARE, etc.) and increase school-based programs. Apply for grants. Work with the health education classes. | HCHC / Compass | Schools, Pharmacies, Providers, Law Enforcement, GVMH, Chambers, Cities, Counties, MO, Schools, Colleges, WCCAA | 01/01/22 - 12/31/22 |  | 4547 | 2000 | 1716 | 1590 | 7000 | 16853 | **City hours; **Coalition grants. HCHC provided Anti Vaping education in Henry County Schools.
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Research prevalent issues leading to drug abuse by adolescents. Continue to develop meaningful community youth activities which deter them from the research findings. | [5 empty] | 500 |  |  |  | 500
|  | c | Build recovery support system partners. Create programs to help addicts and their families. Continue to provide counseling and support for drug abusers and their families. Support local substance abuse counseling. Educate public on signs of drug abuse and how to approach those needing guidance. | [8 empty] | 7000 | 7000 | **Coalition grants
|  | d | Monitor prescription drug abuse. Support PSA providers in discouraging prescription drug abuse. Create an alert system between providers and pharmacies for drug abuse. | GVMH |  | 2021-06-01 | 750 |  | 1000 |  |  |  | 1750 | PDMP is being utilized in Henry and Benton County.
|  | e | Investigate grant writing to fund drug abuse education/counseling. If available, designate community lead to work to attain the necessary grant. | [9 empty] | 0
|  | f | Promote discarding old prescriptions (prescription take-backs) at local police departments, especially opioids. | City / Law Enforcement | [5 empty] | 500 |  |  | 500 | **Clinton Place Dept. time
|  | g | Continue to develop pain management programs. Meet with partners to assess the current needs and initiatives. Continue to educate providers on alternative pain control resources. | [9 empty] | 0
|  | h | Continue to promote recovery court in PSA Clinics. Expand this service to Benton County. | [6 empty] | 3250 |  |  | 3250 | **Clinton Place Dept. time
|  | i | Continue to improve access to suboxone treatment services. |  |  | 01/01/20 - 12/31/20 |  | 427974 |  |  |  |  | 427974 | Expended Grant
|  | j | Continue to utilize HCHC grant funding to set programs up in schools in PSA. |  |  | 2021 |  |  | 4000 |  |  |  | 4000 | Programs in place at three HC Schools
|  | k | Expand screening brief intervention referral and treatment (SBIRT). Promote evidence-based interventions. | [9 empty] | 0
4 | Lack of Inpatient Psychiatric beds | a | Implement ERE program at GVMH to benefit residents in the PSA. | Compass/GVMH | Law Enforcement (CIT), MO, Providers, Royal Oaks, |  | 32000 | [5 empty] | 32000
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Retain existing psychiatric providers and determine if additional providers should be recruited. | GVMH/Compass |  | 01/01/21 - 12/31/21 | 110000 | [5 empty] | 110000 | GVMH actively recruiting behavioral health and psych provider
|  | c | Continue to recruit providers to area. Utilize national recruiters to find quality providers. | GVMH/Compass |  | 01/01/2022 - 12/31/2022 | 30000 | [5 empty] | 30000 | Focus on LCSW recruitment and evaluate second mid-level
|  | d | Expand Inpatient adult/geriatric behavioral services. | Compass | [8 empty] | 0
|  | e | Continue to promote Royal Oaks Hospital (54+ beds) in Windsor. Utilize their services within both counties. | Compass | [8 empty] | 0
|  | f | Continue to seek MO grant to help fund the diversion center. | Compass | [8 empty] | 0
|  | g | Explore WCCAA partners for transitional (step down) housing (MO Dept. of MH). | WCMCAA | [8 empty] | 0
|  | h | Launch crisis intervention training classes to help community members/providers and law enforcement secure their certification. | Law Enforcement/City | [8 empty] | 0
5 | Obesity (Nutrition / Exercise) / Food Insecurity | a | Collaborate with health plans, local cities and other groups focused on fitness, healthy eating and access to fresh fruits and vegetables. | HCHC / MU Ext | WCCAA, Harvesters, GVMH, Schools, Colleges, Cities, Counties, Clergy, Chambers, Kaysinger Basin, WIC, Fitness Centers, Compass, 4H Clubs, Samaritan Center | 01/01/2022 - 12/31/2022 | [6 empty] | 0 | HCHC Board approved three initiatives for HCHC to work on regarding obesity prevention. Programs are in place and on-going
|  | b | Grow and promote community farmer's market. Offer gardening classes. Support “farm to school” program to provide local produce to students. | WCMCAA | [7 empty] | 15000 | 15000
|  | c | Expand free cooking classes to community. Create and publish healthy low cost recipe book outlining healthy dinners and/or dining with diabetes/food restrictions. | MU Ext |  |  |  |  | 2000 |  |  |  | 2000
|  | d | Create and promote a community garden where locals can grow their own food to decrease meal costs and increase healthy eating. | [9 empty] | 0
|  | e | Develop support for local food bank and/or other food giveaway options. | [9 empty] | 0
|  | f | Educate and expand youth physical activity programs. Create after school programs to keep youth active. | Samaritan Center |  | 01/01/2022 - 12/31/2022 | 50000 |  | 1500 | 304662 |  | 60000 | 416162 | GVMH commitment to the inclusive playground
|  | g | Establish relationship with schools to provide education to students and families about health eating strategies. Encourage healthy after school snacking. | Schools/MU Ext |  |  |  |  | 550 |  |  |  | 550
|  | h | Continue to promote community health. Create effective media (i.e. print, radio, digital). Continue to provide education to the community through health fairs and educational programs, including various screenings. | Compass |  |  |  |  | 3000 |  |  |  | 3000
|  | i | Expand the community wellness committee's (CWC) initiatives previously established and help implement the strategy. | ALL |  | 01/01/2022 - 12/31/2022 | [6 empty] | 0 | HCHC instituted the Healthy Streets initiative and has an active advisory council working on the goals
|  | j | Continue the wellness incentive for GVMH, HCHC and Compass employees and launch "staff health" challenge. Continue to offer healthy food options on campus. | ALL |  |  |  | 110000 | 450 | 3182 |  |  | 113632 | **City program
|  | k | Continue with nutritional education classes (MU Ext), nutrition services (OP GVMH), and IP Compass services. | ALL | [8 empty] | 0
|  | l | Continue the "Commit to Fit" community-wide fitness challenge initiative focusing on fitness, nutrition and physical activity. | ALL |  | 01/01/20 - 12/31/20 | 2000 |  | 800 |  |  |  | 2800 | Completed in 2020
|  | m | Continue to promote WIC and food stamp programs. Continue with school back-pack program. Expand "No Kid Hungry" initiative in Clinton schools. Expand program into Benton County. | Samaritan Center |  |  |  |  | 500 |  |  |  | 500
|  | n | Continue and encourage other schools to provide healthier options in school vending machines. | Schools | [8 empty] | 0
|  | o | Continue with Henry county home program "Building Community for Better Health Access to Healthy Foods" through the Community Coalition. Build "Girls on the Run" program. | HCHC |  | 01/01/20 - 12/31/20 ONLY |  |  | 1000 |  |  |  | 1000 | BCBH has continued and Healthy Streets is a subcommittee of this program. GOTR was disbanded due to the high membership fee's by CHART..
6 | Poor Health Insurance (Lack of Coverage) | a | Expand marketplace enrollment assistance education. Help residents enroll into Medicaid/ACA insurance coverage. Utilize Compass outreach representative to help students sign up for Medicaid. | Compass/HCHC/GVMH | Chambers, Cities, Counties, WIC, MO, | 01/01/22 - 12/31/22 | 53000 | 33346 | 500 |  |  |  | 86846 | Medicaid Expansion in MO rolled out in 2021. Enrollment will occur 2022
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Start proactive MO Medicaid pass campaign. Continue to host public meetings to educate community on health reform law's insurance coverage options. | HCHC 2021 |  | 01/01/22 -12/31/22 | [6 empty] | 0 | One HCHC staff member is certified in providing insurance counseling.
|  | c | Partnering with surrounding hospitals to advocate for Medicaid expansion. Mobilize hard to reach populations. | ALL |  | 01/01/20 -11/17/20 |  |  | 1700 |  |  |  | 1700
|  | d | Provide education class to public and community in regards to how to properly navigate using health insurance coverage properly. | ALL | [8 empty] | 0
|  | e | Continue to offer informative meetings at GVMH and sliding scale options at Compass and GVMH. Provide payment assistance programs to persons who have healthcare needs | GVMH |  | 01/01/2022 - 12/31/2022 | 1000000 | [5 empty] | 1000000 | Exceeded commitment. Will repeat for 2021 and 2022
|  | f | Research federal assistant for health insurance policies for rural health organizations. Investigate Trump community Insurance pools. | ALL | [8 empty] | 0
|  | g | Continue to offer and promote the Clinton Chamber's "group plan options." | Chamber (Clinton) | [7 empty] | 2500 | 2500
7 | Housing (Safe and Affordable) | a | Create a county housing development plan that would address affordable safe housing for community residents. Complete Henry and Benton county-wide housing study. | Cities of Warsaw/Clinton | WCCAA, HCHC, Counties, Compass, GVMH, Chambers, Harvesters, Kaysinger Basin, MU Ext, Schools, Colleges |  |  | 54000 |  |  |  | 14304 | 68304 | ** Annual Dev Budget - WCMCAA, Henry Co
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Explore and create a Habitat for Humanity-type process in Henry and Benton county area. | ALL | [8 empty] | 0
|  | c | Develop policies that set standards for rental properties and maintaining housing in PSA. Explore the set up of safe rental inspections. Utilize "Weatherization" with WCMCAA. | WCMCAA (2 Co) | [7 empty] | 80000 | 80000
|  | d | Investigate grant writing to fund public/safe housing. If available, designate community lead to work to attain the necessary grant. | Nap Grant | [7 empty] | 20000 | 20000
|  | e | Target infill development of existing infrastructures to encourage affordable home ownership. | WCMCAA (2 Co) | [7 empty] | 792408 | 792408 | **Multi-Family Housing Annual Budget - WCMCAA, Henry Co and Benton Co
8 | Transportation | a | Continue to research current transportation resources and gaps. Expand search to non-motorized transportation options. | WCCAA | Compass, GVMH, HCHC, MO, Cities, Law Enforcement (CIT), Counties, Schools, Colleges | [7 empty] | 0
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Develop and publish Henry/Benton counties transportation master plan. Track results annually. | [9 empty] | 0
|  | c | Communicate to the public what transportation services are available through mass media, online, digital and at businesses in two counties. |  |  | 01/01/2022 - 12/31/2022 | 1400 | [5 empty] | 1400
|  | d | Explore transportation grants for Henry and Benton county. |  |  | 01/01/2022 - 12/31/2022 | 2600 | 90000 |  | 69163 |  |  | 161763 | **City MODOT grant
|  | e | Identify home-based monitoring programs for healthcare service offerings. Encourage local payers to cover the monitoring. |  |  | 01/01/2022-12/31/2022 | 45000 |  |  |  |  | 10000 | 55000 | Software has been purchased and staff being trained for roll out soon
|  | f | Continue to utilize OATS, ALS-City, HealthTran, Compass services, Dental Bus and others. |  |  | 01/01/22 - 12/31/22 | 27000 | 200000 |  | 69163 |  |  | 296163 | Program initiated.
|  |  | Total Annual Contributions |  |  |  | 1410950 | 2387849 | 19500 | 550636 | 2090 | 1009062 | 5380087
**Please Note: Compass Health Network funding is as follows: 1) Outreach and Enrollment $22,693 split (.5 FTE) for 1a $11,346 and 6a $11,346 plus $22,000; 2) MAT Dr Time $194,610 (.5 FTE) plus $174,364 (.5 FTE) for 3i plus $59,000; 3) Prevention Time $14,941 (.3 FTE) plus $3,249 (.08 FTE) total ($18,190) split by 1e ($4,547), 1f ($4,547), 1m ($4,547) and 3a ($4,547); 4) CMHL total $16,413 (.25 FTE) for 1i; and 5) Mental Health First Aid time $2,291 (.05 FTE) for 1e plus $6,838.

## StakeholdersKEY_Emails
Henry & Benton Co, Missouri Stakeholders
KEY | Name | Contact | Email
4H Clubs | 4H Clubs - local (Henry county through MU Ext.) | Henry County 4-H Council officers: Co-Presidents -- Brendon Engeman and Jessalyn Caple (MU Ext- Susan Jones-Hard) | MU Ext email
Chambers | Clinton Chamber of Commerce or City of Warsaw | Mark Dawson- Economic Dev Director; Debby VanWinkle- Chamber Director, Clinton; Warsaw Chamber | mark@clintonmo.com; debby@clintonmo.com; warsawchamber@outlook.com
Cities | Clinton, Warsaw | Clinton - Christina Maggi, Warsaw - Randy Pogue | cmaggi@cityofclintonmo.com; randy.pogue@welcometowarsaw.com
Clergy | Ministerial alliance | Clinton UMC | office@clintonumc.net
Colleges | SFCC, UM, CM | Tammy Woirhaye - SFCC | twoirhaye@sfccmo.edu
Compass | Compass Health Network (Henry and Benton) | Donni Kuck, Saundra Overton, others | dkuck@compasshn.org; soverton@compasshn.org
Counties | Henry and Benton County, MO
Ec Dev | Economic Development - Clinton | Mark Dawson | mark@clintonmo.com
Fitness Centers | PSA Community Center
GVMH | Golden Valley Memorial Healthcare | Craig Thompson, others | cthompson@gvmh.org
Harvesters | PSA Harvesters (26 county area) | Sheila Barkwell - The Samaritan Center | The Samaritan Center email
HCHC | Henry County Health Center (including WIC) | Peggy Bowles, Kayla Meads, others | peggy.bowles@lpha.mo.gov
Kaysinger Basin | 7 counties (Bates, Benton, Cedar, Henry, Hickory, St Clair and Vernon) (state initiative) Kaysinger Basin Regional Planning Commission | Ex Dir - Sheridan Garman-Neeman, Henry county - Dale Lawler, Benton county - Steve Daleske | sgarman@kaysinger.com
Law Enforcement | PSA city and counties law enforcement (CIT training), Henry County Sheriff's office - Clinton | Chad Nepple - CPD, Rob Hills | c.nepple@clintonmopd.com; rob170k9@gmail.com
MO - State | State of Missouri
MU Ext | Missouri University Extension Office | Susan Jones-Hard | joneshards@missouri.edu
Pharmacies | PSA pharmacies
Providers | PSA providers of healthcare
Royal Oaks | Royal Oaks Hospital (Compass) | Erin Allen, Erica Jenkins, others | ejenkins@compasshn.org
Samaritan Center | Samaritan Center - Clinton | Sheila Barkwell | director@clintonsamaritancenter.com
Schools | Clinton Schools, PSA schools | Teresa Howard (social work), Stacy Pitts, Michelle Henzlik- Clinton Intermediate, Angie Lawson, Jamie McCoy- Clinton HS Counselor, Makenna Hix, Sherri Swope (Principal) | thoward@clintoncardinals.org; spitts@clintoncardinals.org; mhenzlik@clintoncardinals.org; alawson@clintoncardinals.org; jamccoy@clintoncardinals.org; mhix@clintoncardinals.org
WCCAA | West Central Missouri Community Action Agency | Kristina Klass, Linda Schreck, Patty Cantrell - New Growth, Kelly Ast | kklass@wcmcaa.org; lschreck@wcmcaa.org; pcantrell@newgrowthmo.org; Kast@wcmcaa.org